Exploration Disturbance Management Plan

Nov 2025

DISTRIBUTION CONTROLLED –NEXT REVIEW DATE 30/06/2025

| NAME | POSITION | COMPANY | RESPONSIBLE FOR | DATE | SIGNATURE |
| --- | --- | --- | --- | --- | --- |
| I Gregory | Geology Manager | Medallion Metals | Revision | Nov 25 |  |
| Phillip Fox | Exploration Manager | Medallion Metals | Revision | August 2024 |  |
| Claire Edwards | Senior Geologist | Medallion Metals | Author | July 2024 |  |

Table of Contents

1.	Purpose	3

2.	Summary of Phases	4

Table 1 Ground Disturbance & Rehabilitation Overview	3

Table 2 Planning Process	5

Table 3 Clearing Process	6

Table 4 Pre-Rehabilitation	7

Table 5 Rehabilitation Works	8

Table 6 Post Rehabilitation	9

# Purpose

The purpose of this management plan is to ensure that staff and contractors are familiar with the procedures necessary to conduct ground disturbing activities on Medallion Metals tenements. It aims to highlight the steps, the estimated timeframes and the  positions responsible for each stage of the plan. (Table 1).

This management plan refers to Medallion’s existing Standard Operating Procedures (SOP) MED_023 – Clearing of drill lines, MED_024 – Rehabilitation and MED_036 – Dieback Management Plan.

Intent

- To ensure Medallion Ground Disturbance Activities are completed in compliance with DEMIRS approvals and Mining Regulations.

- Provide specific instructions for undertaking ground disturbance

- To ensure an approval system is in place

- To ensure that ground disturbance is approved and authorised to proceed

- To document and record Ground Disturbance effectively

Table 1 Ground Disturbance & Rehabilitation Overview

# Summary of Phases

Drill Planning & POW Application / Approval (Table 2)

The planning phase is including steps to engage with various stakeholders to ensure that disturbance and impact are minimised. A number of steps and approvals, both internal and external to Medallion need to be completed prior to commencement of physical site preparation and clearing.

Medallion’s tenements are located in an environmentally sensitive area. Due to this, exploring in the region requires comprehensive planning 12-18 months in advance of the actual planned activity. In some instances, Medallion is required to complete local targeted ecological surveys which then need to be put into regional context. There are limitations on when and how these surveys are conducted due to seasonal and climatic factors.

Clearing – (Table 3)

Tenement conditions require an approved PoW before commencing site preparation and clearing. When a PoW has been approved, Medallion geologists will issue a Ground Disturbance Plan (GDP). A GDP is completed to communicate which drill sites and access tracks are approved to be cleared. A GDP requires approval from the Exploration Manager. The clearing phase includes validation steps prior to physical disturbance occurring to ensure adherence to the PoW and minimise the impact of planned disturbance. (MED_023)

Table 3 outlines the specific steps required to clear sites.

Ground Disturbance Approval Documents consists of;

- GDP Document issued, approved by the Exploration Manager or delegate

- GDP Hole/ Pad Site List (spreadsheet) Pad ID / Hole ID , POW, buffer zones

- GDP Map and Shapefiles with Pads to be cleared.

- Shapefiles for the GDP loaded into QGIS for checking co-ordinates

- Site Docs Form – used to record the field checks within the GDP Document

- File Naming Convention for all related files - ‘GPD_YYYYMMDD_[Program name]’

Important notes

- The POW pads, sizes and tracks provided in the GPD need to be closely adhered to.

- Mark out the areas to be cleared using the DGP / Qfield to accurately locate and guide clearing within ~ 2m of the GDP pad co-ordinates provided, using DGPS

- Do not clear areas that are not within the supplied within the GDP maps & Shapefiles

- Some pads are in previously rehabilitated areas, do not over-clear these areas, adhere to the approved POW; a POW may not be in place over these areas adjacent to the specific pad.

- If in doubt- do not clear and check with the Geology Supervisor at Site

Pre-Rehabilitation - Execution and Data Requirements– (Table 4)

After drilling has been completed at any individual site, data collection such as sampling, re-sampling, receival of results, any downhole surveying and drill collar surveys must be completed prior to rehabilitation of the site. This phase is the data collection phase. The timeline for this phase can vary due to wet weather (MED_036), lab turnaround times, drill results and geological observations etc.,

Rehabilitation – (Table 5)

The current deadline for completion of rehabilitation works is 12 months post-completion of the ground-disturbing activity. (MED_024) The timeline for this phase can vary due to data return and the possibility of additional sampling or re-sampling requirements, and seasonal weather conditions .ie wet conditions. (MED_036). Recording of key dates is required to track progress and inform Exploration Manager of requirements for extension if required.

Post Rehabilitation and Monitoring – (Table 6)

Medallion are required to report annually disturbance and rehabilitation status across all tenements. The Annual Environment Report (AER) is due in January of each year and Mine Rehabilitation Fund (MRF) in June.

Medallion are required to monitor and record progress of rehabilitation. Drill holes with hole name ending in either a ‘0’ or a ‘5’ will be captured by photo image as per Medallions rehabilitation procedure (MED_024). This is deemed to be representative for this purpose.

Table 2 Planning Process

CP = Checkpoint

Table 3 Clearing Process

Table 4 Pre-Rehabilitation

Drill pad can be released for full rehabilitation after all data has been received.

Table 5 Rehabilitation Works

Rehabilitation is required within a 12-month period. In case of delays to rehabilitation activities ie wet conditions, an extension will need to be sought from DMIRS.

Table 6 Post Rehabilitation